## City wise
Row Labels | Approved | issued building permit | Agreement executed | Started | 2nd | 3rd | Completed | Started %against approved | Completed % against approved
Mukkom | 376 | 360 | 350 | 348 | 331 | 294 | 176 | 92.55% | 46.81%
Feroke | 407 | 357 | 337 | 331 | 222 | 162 | 11 | 81.33% | 2.703%
Payyannur | 623 | 517 | 508 | 505 | 369 | 180 | 48 | 81.06% | 7.705%
Thalipparamba | 291 | 226 | 227 | 227 | 200 | 140 | 69 | 78.01% | 23.71%
Anthoor | 376 | 290 | 290 | 290 | 239 | 180 | 65 | 77.13% | 17.29%
Adoor | 158 | 121 | 121 | 121 | 70 | 42 | 10 | 76.58% | 6.329%
Mattannur | 356 | 280 | 269 | 269 | 225 | 129 | 14 | 75.56% | 3.933%
Mannarkkad | 592 | 494 | 491 | 442 | 119 | 116 | 86 | 74.66% | 14.53%
Irinjalakuda | 550 | 407 | 407 | 407 | 336 | 210 | 85 | 74% | 15.45%
Kalpetta | 537 | 402 | 394 | 394 | 241 | 184 | 91 | 73.37% | 16.95%
Varkala | 422 | 313 | 313 | 309 | 260 | 210 | 97 | 73.22% | 22.99%
Attingal | 179 | 149 | 141 | 129 | 116 | 78 | 30 | 72.07% | 16.76%
Pattambi | 504 | 350 | 350 | 350 | 297 | 173 | 34 | 69.44% | 6.746%
Kannur | 940 | 663 | 649 | 649 | 325 | 214 | 86 | 69.04% | 9.149%
Ramanattukara | 242 | 168 | 168 | 165 | 137 | 91 | 5 | 68.18% | 2.066%
Chalakudy | 341 | 238 | 229 | 229 | 159 | 108 | 41 | 67.16% | 12.02%
Koduvally | 785 | 548 | 548 | 516 | 339 | 152 | 4 | 65.73% | 0.5096%
South Paravoor | 596 | 445 | 445 | 390 | 334 | 257 | 134 | 65.44% | 22.48%
Piravom | 245 | 162 | 160 | 160 | 111 | 99 | 13 | 65.31% | 5.306%
Cherthala | 521 | 341 | 341 | 337 | 224 | 118 | 18 | 64.68% | 3.455%
Valanchery | 417 | 298 | 270 | 263 | 122 | 99 | 5 | 63.07% | 1.199%
Angamaly | 131 | 85 | 82 | 82 | 67 | 45 | 18 | 62.6% | 13.74%
Thalassery | 302 | 196 | 188 | 187 | 141 | 103 | 36 | 61.92% | 11.92%
Thodupuzha | 932 | 606 | 576 | 576 | 385 | 336 | 206 | 61.8% | 22.1%
Guruvayoor | 678 | 443 | 443 | 413 | 267 | 176 | 50 | 60.91% | 7.375%
Perumbavoor | 139 | 59 | 88 | 84 | 71 | 54 | 21 | 60.43% | 15.11%
Ettumanoor | 389 | 239 | 239 | 235 | 167 | 120 | 51 | 60.41% | 13.11%
Vaikom | 199 | 132 | 132 | 120 | 80 | 63 | 6 | 60.3% | 3.015%
Kayamkulam | 704 | 450 | 436 | 424 | 338 | 257 | 169 | 60.23% | 24.01%
Malappuram | 1469 | 976 | 976 | 878 | 606 | 448 | 136 | 59.77% | 9.258%
Palai | 75 | 70 | 70 | 44 | 26 | 20 | 6 | 58.67% | 8%
Kottarakkara | 404 | 290 | 267 | 237 | 134 | 98 | 13 | 58.66% | 3.218%
Shoranur | 713 | 462 | 448 | 410 | 250 | 94 | 22 | 57.5% | 3.086%
Koothuparamba | 410 | 248 | 239 | 235 | 179 | 140 | 32 | 57.32% | 7.805%
Chittur-Thathamangalam | 618 | 358 | 354 | 354 | 240 | 179 | 49 | 57.28% | 7.929%
Panoor | 423 | 250 | 243 | 241 | 176 | 89 | 14 | 56.97% | 3.31%
Kondotty | 842 | 499 | 476 | 476 | 332 | 273 | 140 | 56.53% | 16.63%
Koohtattukulam | 276 | 157 | 155 | 155 | 104 | 90 | 32 | 56.16% | 11.59%
Vadakara | 542 | 311 | 118 | 304 | 221 | 118 | 18 | 56.09% | 3.321%
Cherplassery | 474 | 348 | 264 | 264 | 96 | 95 | 48 | 55.7% | 10.13%
Muvattupuzha | 176 | 96 | 96 | 96 | 85 | 77 | 48 | 54.55% | 27.27%
Manjeri | 1476 | 1151 | 1151 | 801 | 499 | 379 | 44 | 54.27% | 2.981%
Kottakkal | 244 | 138 | 137 | 132 | 123 | 52 | 4 | 54.1% | 1.639%
Thiruvananthapuram | 7877 | 5106 | 4967 | 4231 | 2404 | 1053 | 125 | 53.71% | 1.587%
Mavelikkara | 202 | 131 | 113 | 108 | 90 | 71 | 36 | 53.47% | 17.82%
Kottayam | 678 | 366 | 363 | 361 | 287 | 218 | 76 | 53.24% | 11.21%
Eloor | 148 | 82 | 78 | 78 | 55 | 45 | 18 | 52.7% | 12.16%
Karunagappally | 562 | 336 | 336 | 293 | 168 | 108 | 70 | 52.14% | 12.46%
Punalur | 1155 | 912 | 910 | 585 | 176 | 171 | 112 | 50.65% | 9.697%
Thrikakara | 245 | 136 | 124 | 124 | 109 | 92 | 50 | 50.61% | 20.41%
Kanhangad | 1150 | 595 | 584 | 580 | 421 | 223 | 47 | 50.43% | 4.087%
Kunnamkulam | 1095 | 606 | 596 | 552 | 233 | 132 | 35 | 50.41% | 3.196%
Nilambur | 372 | 196 | 196 | 187 | 101 | 55 | 9 | 50.27% | 2.419%
Kattapana | 1378 | 717 | 717 | 685 | 454 | 350 | 115 | 49.71% | 8.345%
Nedumangadu | 2338 | 1228 | 1140 | 1140 | 758 | 722 | 500 | 48.76% | 21.39%
Sreekandapuram | 520 | 361 | 358 | 253 | 179 | 127 | 30 | 48.65% | 5.769%
Ponnani | 1376 | 718 | 691 | 658 | 443 | 315 | 79 | 47.82% | 5.741%
Wadakkanchery | 1484 | 940 | 901 | 709 | 493 | 310 | 35 | 47.78% | 2.358%
Thrissur | 994 | 532 | 472 | 472 | 391 | 308 | 126 | 47.48% | 12.68%
Chavakkad | 888 | 415 | 412 | 412 | 361 | 315 | 110 | 46.4% | 12.39%
Kollam | 4113 | 2094 | 1810 | 1900 | 1431 | 1090 | 650 | 46.19% | 15.8%
Neyyattinkara | 2168 | 1188 | 1171 | 980 | 521 | 416 | 219 | 45.2% | 10.1%
N.Paravur | 305 | 187 | 144 | 135 | 117 | 85 | 34 | 44.26% | 11.15%
Aluva | 63 | 28 | 28 | 27 | 20 | 13 | 5 | 42.86% | 7.937%
Tirurangadi | 396 | 183 | 178 | 167 | 131 | 40 | 9 | 42.17% | 2.273%
Kalamassery | 641 | 292 | 279 | 269 | 191 | 162 | 90 | 41.97% | 14.04%
Changanassery | 248 | 104 | 104 | 104 | 57 | 40 | 6 | 41.94% | 2.419%
Quilandy | 946 | 422 | 411 | 395 | 290 | 173 | 5 | 41.75% | 0.5285%
Ottappalam | 899 | 575 | 593 | 371 | 290 | 245 | 79 | 41.27% | 8.788%
Palakkad | 1872 | 841 | 767 | 754 | 511 | 345 | 85 | 40.28% | 4.541%
Thripunithura | 761 | 305 | 305 | 305 | 258 | 230 | 100 | 40.08% | 13.14%
Thiruvalla | 410 | 163 | 163 | 163 | 128 | 95 | 33 | 39.76% | 8.049%
Thanur | 1676 | 730 | 730 | 662 | 344 | 50 | 0 | 39.5% | 0%
Irritty | 471 | 220 | 192 | 186 | 116 | 60 | 11 | 39.49% | 2.335%
Maradu | 446 | 211 | 211 | 172 | 160 | 140 | 66 | 38.57% | 14.8%
Pathanamthitta | 649 | 288 | 265 | 242 | 173 | 128 | 80 | 37.29% | 12.33%
Chengannur | 144 | 63 | 56 | 53 | 35 | 16 | 3 | 36.81% | 2.083%
Nileswaram | 686 | 337 | 255 | 251 | 155 | 100 | 10 | 36.59% | 1.458%
Kochi | 4784 | 1753 | 1717 | 1628 | 1128 | 919 | 412 | 34.03% | 8.612%
Kodungallur | 1069 | 589 | 502 | 357 | 231 | 181 | 83 | 33.4% | 7.764%
Haripad | 390 | 229 | 165 | 130 | 45 | 12 | 1 | 33.33% | 0.2564%
Kozhikode | 3009 | 1172 | 1002 | 994 | 511 | 310 | 43 | 33.03% | 1.429%
Alappuzha | 3779 | 2018 | 1902 | 1236 | 931 | 685 | 89 | 32.71% | 2.355%
Kasaragod | 362 | 126 | 126 | 109 | 88 | 75 | 23 | 30.11% | 6.354%
Pandalam | 674 | 322 | 287 | 194 | 130 | 101 | 5 | 28.78% | 0.7418%
Mananthavady | 1888 | 535 | 524 | 504 | 267 | 133 | 35 | 26.69% | 1.854%
Kothamangalam | 619 | 173 | 170 | 165 | 124 | 83 | 28 | 26.66% | 4.523%
Payyoli | 787 | 214 | 211 | 208 | 81 | 27 | 2 | 26.43% | 0.2541%
Sulthan Bathery | 978 | 376 | 347 | 245 | 182 | 97 | 5 | 25.05% | 0.5112%
Perinthalmanna | 1374 | 382 | 362 | 324 | 171 | 94 | 8 | 23.58% | 0.5822%
Tirur | 708 | 209 | 201 | 165 | 110 | 55 | 14 | 23.31% | 1.977%
Parappanangady | 931 | 372 | 372 | 190 | 73 | 23 | 2 | 20.41% | 0.2148%
Erattupetta | 705 | 473 | 473 | 141 | 140 | 140 | 66 | 20% | 9.362%
| 82487 | 45244 | 43167 | 38733 | 25626 | 17520 | 6159 | 46.96% | 7.467%
Row Labels | Approved | issued building permit | Agreement executed | Started | 2nd | 3rd | Completed | Started %against approved | Completed % against approved
Mukkom | 376 | 360 | 350 | 348 | 331 | 294 | 176 | 92.55% | 46.81%
Muvattupuzha | 176 | 96 | 96 | 96 | 85 | 77 | 48 | 54.55% | 27.27%
Kayamkulam | 704 | 450 | 436 | 424 | 338 | 257 | 169 | 60.23% | 24.01%
Thalipparamba | 291 | 226 | 227 | 227 | 200 | 140 | 69 | 78.01% | 23.71%
Varkala | 422 | 313 | 313 | 309 | 260 | 210 | 97 | 73.22% | 22.99%
South Paravoor | 596 | 445 | 445 | 390 | 334 | 257 | 134 | 65.44% | 22.48%
Thodupuzha | 932 | 606 | 576 | 576 | 385 | 336 | 206 | 61.8% | 22.1%
Nedumangadu | 2338 | 1228 | 1140 | 1140 | 758 | 722 | 500 | 48.76% | 21.39%
Thrikakara | 245 | 136 | 124 | 124 | 109 | 92 | 50 | 50.61% | 20.41%
Mavelikkara | 202 | 131 | 113 | 108 | 90 | 71 | 36 | 53.47% | 17.82%
Anthoor | 376 | 290 | 290 | 290 | 239 | 180 | 65 | 77.13% | 17.29%
Kalpetta | 537 | 402 | 394 | 394 | 241 | 184 | 91 | 73.37% | 16.95%
Attingal | 179 | 149 | 141 | 129 | 116 | 78 | 30 | 72.07% | 16.76%
Kondotty | 842 | 499 | 476 | 476 | 332 | 273 | 140 | 56.53% | 16.63%
Kollam | 4113 | 2094 | 1810 | 1900 | 1431 | 1090 | 650 | 46.19% | 15.8%
Irinjalakuda | 550 | 407 | 407 | 407 | 336 | 210 | 85 | 74% | 15.45%
Perumbavoor | 139 | 59 | 88 | 84 | 71 | 54 | 21 | 60.43% | 15.11%
Maradu | 446 | 211 | 211 | 172 | 160 | 140 | 66 | 38.57% | 14.8%
Mannarkkad | 592 | 494 | 491 | 442 | 119 | 116 | 86 | 74.66% | 14.53%
Kalamassery | 641 | 292 | 279 | 269 | 191 | 162 | 90 | 41.97% | 14.04%
Angamaly | 131 | 85 | 82 | 82 | 67 | 45 | 18 | 62.6% | 13.74%
Thripunithura | 761 | 305 | 305 | 305 | 258 | 230 | 100 | 40.08% | 13.14%
Ettumanoor | 389 | 239 | 239 | 235 | 167 | 120 | 51 | 60.41% | 13.11%
Thrissur | 994 | 532 | 472 | 472 | 391 | 308 | 126 | 47.48% | 12.68%
Karunagappally | 562 | 336 | 336 | 293 | 168 | 108 | 70 | 52.14% | 12.46%
Chavakkad | 888 | 415 | 412 | 412 | 361 | 315 | 110 | 46.4% | 12.39%
Pathanamthitta | 649 | 288 | 265 | 242 | 173 | 128 | 80 | 37.29% | 12.33%
Eloor | 148 | 82 | 78 | 78 | 55 | 45 | 18 | 52.7% | 12.16%
Chalakudy | 341 | 238 | 229 | 229 | 159 | 108 | 41 | 67.16% | 12.02%
Thalassery | 302 | 196 | 188 | 187 | 141 | 103 | 36 | 61.92% | 11.92%
Koohtattukulam | 276 | 157 | 155 | 155 | 104 | 90 | 32 | 56.16% | 11.59%
Kottayam | 678 | 366 | 363 | 361 | 287 | 218 | 76 | 53.24% | 11.21%
N.Paravur | 305 | 187 | 144 | 135 | 117 | 85 | 34 | 44.26% | 11.15%
Cherplassery | 474 | 348 | 264 | 264 | 96 | 95 | 48 | 55.7% | 10.13%
Neyyattinkara | 2168 | 1188 | 1171 | 980 | 521 | 416 | 219 | 45.2% | 10.1%
Punalur | 1155 | 912 | 910 | 585 | 176 | 171 | 112 | 50.65% | 9.697%
Erattupetta | 705 | 473 | 473 | 141 | 140 | 140 | 66 | 20% | 9.362%
Malappuram | 1469 | 976 | 976 | 878 | 606 | 448 | 136 | 59.77% | 9.258%
Kannur | 940 | 663 | 649 | 649 | 325 | 214 | 86 | 69.04% | 9.149%
Ottappalam | 899 | 575 | 593 | 371 | 290 | 245 | 79 | 41.27% | 8.788%
Kochi | 4784 | 1753 | 1717 | 1628 | 1128 | 919 | 412 | 34.03% | 8.612%
Kattapana | 1378 | 717 | 717 | 685 | 454 | 350 | 115 | 49.71% | 8.345%
Thiruvalla | 410 | 163 | 163 | 163 | 128 | 95 | 33 | 39.76% | 8.049%
Palai | 75 | 70 | 70 | 44 | 26 | 20 | 6 | 58.67% | 8%
Aluva | 63 | 28 | 28 | 27 | 20 | 13 | 5 | 42.86% | 7.937%
Chittur-Thathamangalam | 618 | 358 | 354 | 354 | 240 | 179 | 49 | 57.28% | 7.929%
Koothuparamba | 410 | 248 | 239 | 235 | 179 | 140 | 32 | 57.32% | 7.805%
Kodungallur | 1069 | 589 | 502 | 357 | 231 | 181 | 83 | 33.4% | 7.764%
Payyannur | 623 | 517 | 508 | 505 | 369 | 180 | 48 | 81.06% | 7.705%
Guruvayoor | 678 | 443 | 443 | 413 | 267 | 176 | 50 | 60.91% | 7.375%
Pattambi | 504 | 350 | 350 | 350 | 297 | 173 | 34 | 69.44% | 6.746%
Kasaragod | 362 | 126 | 126 | 109 | 88 | 75 | 23 | 30.11% | 6.354%
Adoor | 158 | 121 | 121 | 121 | 70 | 42 | 10 | 76.58% | 6.329%
Sreekandapuram | 520 | 361 | 358 | 253 | 179 | 127 | 30 | 48.65% | 5.769%
Ponnani | 1376 | 718 | 691 | 658 | 443 | 315 | 79 | 47.82% | 5.741%
Piravom | 245 | 162 | 160 | 160 | 111 | 99 | 13 | 65.31% | 5.306%
Palakkad | 1872 | 841 | 767 | 754 | 511 | 345 | 85 | 40.28% | 4.541%
Kothamangalam | 619 | 173 | 170 | 165 | 124 | 83 | 28 | 26.66% | 4.523%
Kanhangad | 1150 | 595 | 584 | 580 | 421 | 223 | 47 | 50.43% | 4.087%
Mattannur | 356 | 280 | 269 | 269 | 225 | 129 | 14 | 75.56% | 3.933%
Cherthala | 521 | 341 | 341 | 337 | 224 | 118 | 18 | 64.68% | 3.455%
Vadakara | 542 | 311 | 118 | 304 | 221 | 118 | 18 | 56.09% | 3.321%
Panoor | 423 | 250 | 243 | 241 | 176 | 89 | 14 | 56.97% | 3.31%
Kottarakkara | 404 | 290 | 267 | 237 | 134 | 98 | 13 | 58.66% | 3.218%
Kunnamkulam | 1095 | 606 | 596 | 552 | 233 | 132 | 35 | 50.41% | 3.196%
Shoranur | 713 | 462 | 448 | 410 | 250 | 94 | 22 | 57.5% | 3.086%
Vaikom | 199 | 132 | 132 | 120 | 80 | 63 | 6 | 60.3% | 3.015%
Manjeri | 1476 | 1151 | 1151 | 801 | 499 | 379 | 44 | 54.27% | 2.981%
Feroke | 407 | 357 | 337 | 331 | 222 | 162 | 11 | 81.33% | 2.703%
Nilambur | 372 | 196 | 196 | 187 | 101 | 55 | 9 | 50.27% | 2.419%
Changanassery | 248 | 104 | 104 | 104 | 57 | 40 | 6 | 41.94% | 2.419%
Wadakkanchery | 1484 | 940 | 901 | 709 | 493 | 310 | 35 | 47.78% | 2.358%
Alappuzha | 3779 | 2018 | 1902 | 1236 | 931 | 685 | 89 | 32.71% | 2.355%
Irritty | 471 | 220 | 192 | 186 | 116 | 60 | 11 | 39.49% | 2.335%
Tirurangadi | 396 | 183 | 178 | 167 | 131 | 40 | 9 | 42.17% | 2.273%
Chengannur | 144 | 63 | 56 | 53 | 35 | 16 | 3 | 36.81% | 2.083%
Ramanattukara | 242 | 168 | 168 | 165 | 137 | 91 | 5 | 68.18% | 2.066%
Tirur | 708 | 209 | 201 | 165 | 110 | 55 | 14 | 23.31% | 1.977%
Mananthavady | 1888 | 535 | 524 | 504 | 267 | 133 | 35 | 26.69% | 1.854%
Kottakkal | 244 | 138 | 137 | 132 | 123 | 52 | 4 | 54.1% | 1.639%
Thiruvananthapuram | 7877 | 5106 | 4967 | 4231 | 2404 | 1053 | 125 | 53.71% | 1.587%
Nileswaram | 686 | 337 | 255 | 251 | 155 | 100 | 10 | 36.59% | 1.458%
Kozhikode | 3009 | 1172 | 1002 | 994 | 511 | 310 | 43 | 33.03% | 1.429%
Valanchery | 417 | 298 | 270 | 263 | 122 | 99 | 5 | 63.07% | 1.199%
Pandalam | 674 | 322 | 287 | 194 | 130 | 101 | 5 | 28.78% | 0.7418%
Perinthalmanna | 1374 | 382 | 362 | 324 | 171 | 94 | 8 | 23.58% | 0.5822%
Quilandy | 946 | 422 | 411 | 395 | 290 | 173 | 5 | 41.75% | 0.5285%
Sulthan Bathery | 978 | 376 | 347 | 245 | 182 | 97 | 5 | 25.05% | 0.5112%
Koduvally | 785 | 548 | 548 | 516 | 339 | 152 | 4 | 65.73% | 0.5096%
Haripad | 390 | 229 | 165 | 130 | 45 | 12 | 1 | 33.33% | 0.2564%
Payyoli | 787 | 214 | 211 | 208 | 81 | 27 | 2 | 26.43% | 0.2541%
Parappanangady | 931 | 372 | 372 | 190 | 73 | 23 | 2 | 20.41% | 0.2148%
Thanur | 1676 | 730 | 730 | 662 | 344 | 50 | 0 | 39.5% | 0%
| 82487 | 45244 | 43167 | 38733 | 25626 | 17520 | 6159 | 46.96% | 7.467%

## District wise
District | Approved | issued building permit | Agreement executed | Started | 2nd | 3rd | Completed | started % | Completed %
Kannur | 4712 | 3251 | 3163 | 3042 | 2149 | 1362 | 405 | 64.56% | 8.595%
Idukki | 2310 | 1323 | 1293 | 1261 | 839 | 686 | 321 | 54.59% | 13.9%
Thiruvananthapuram | 12984 | 7984 | 7732 | 6789 | 4059 | 2479 | 971 | 52.29% | 7.478%
Palakkad | 5672 | 3428 | 3267 | 2945 | 1803 | 1247 | 403 | 51.92% | 7.105%
Thrissur | 7099 | 4170 | 3962 | 3551 | 2471 | 1740 | 565 | 50.02% | 7.959%
Kollam | 6830 | 4077 | 3768 | 3405 | 2243 | 1724 | 979 | 49.85% | 14.33%
Kozhikode | 7094 | 3552 | 3145 | 3261 | 2132 | 1327 | 264 | 45.97% | 3.721%
Kottayam | 2294 | 1384 | 1381 | 1005 | 757 | 601 | 211 | 43.81% | 9.198%
Malappuaram | 11281 | 5852 | 5740 | 4903 | 3055 | 1883 | 450 | 43.46% | 3.989%
Kasaragod | 2198 | 1058 | 965 | 940 | 664 | 398 | 80 | 42.77% | 3.64%
Alappuzha | 5740 | 3232 | 3013 | 2288 | 1663 | 1159 | 316 | 39.86% | 5.505%
Eranakulam | 8979 | 3726 | 3637 | 3480 | 2600 | 2134 | 935 | 38.76% | 10.41%
Pathanamthitta | 1891 | 894 | 836 | 720 | 501 | 366 | 128 | 38.08% | 6.769%
Wayanad | 3403 | 1313 | 1265 | 1143 | 690 | 414 | 131 | 33.59% | 3.85%
Total | 82487 | 45244 | 43167 | 38733 | 25626 | 17520 | 6159 | 47% | 7%
District | Approved | issued building permit | Agreement executed | Started | 2nd | 3rd | Completed | started % | Completed %
Kollam | 6830 | 4077 | 3768 | 3405 | 2243 | 1724 | 979 | 46.96% | 7.467%
Idukki | 2310 | 1323 | 1293 | 1261 | 839 | 686 | 321 | 46.96% | 7.467%
Eranakulam | 8979 | 3726 | 3637 | 3480 | 2600 | 2134 | 935 | 46.96% | 7.467%
Kottayam | 2294 | 1384 | 1381 | 1005 | 757 | 601 | 211 | 46.96% | 7.467%
Kannur | 4712 | 3251 | 3163 | 3042 | 2149 | 1362 | 405 | 46.96% | 7.467%
Thrissur | 7099 | 4170 | 3962 | 3551 | 2471 | 1740 | 565 | 46.96% | 7.467%
Thiruvananthapuram | 12984 | 7984 | 7732 | 6789 | 4059 | 2479 | 971 | 46.96% | 7.467%
Palakkad | 5672 | 3428 | 3267 | 2945 | 1803 | 1247 | 403 | 46.96% | 7.467%
Pathanamthitta | 1891 | 894 | 836 | 720 | 501 | 366 | 128 | 46.96% | 7.467%
Alappuzha | 5740 | 3232 | 3013 | 2288 | 1663 | 1159 | 316 | 46.96% | 7.467%
Malappuaram | 11281 | 5852 | 5740 | 4903 | 3055 | 1883 | 450 | 46.96% | 7.467%
Wayanad | 3403 | 1313 | 1265 | 1143 | 690 | 414 | 131 | 46.96% | 7.467%
Kozhikode | 7094 | 3552 | 3145 | 3261 | 2132 | 1327 | 264 | 46.96% | 7.467%
Kasaragod | 2198 | 1058 | 965 | 940 | 664 | 398 | 80 | 46.96% | 7.467%
Total | 82487 | 45244 | 43167 | 38733 | 25626 | 17520 | 6159 | 46.96% | 7.467%

## Sheet4 (hidden)
City | (All)
Values
Row Labels | Sum of No of beneficiaries | Sum of issued building permit | Sum of Agreement executed | Sum of 1st | Sum of 2nd | Sum of 3rd | Sum of 4th
Alappuzha | 5740 | 3232 | 3013 | 2288 | 1663 | 1159 | 316
Eranakulam | 8979 | 3726 | 3637 | 3480 | 2600 | 2134 | 935
Idukki | 2310 | 1323 | 1293 | 1261 | 839 | 686 | 321
Kannur | 4712 | 3251 | 3163 | 3042 | 2149 | 1362 | 405
Kasaragod | 2198 | 1058 | 965 | 940 | 664 | 398 | 80
Kollam | 6830 | 4077 | 3768 | 3405 | 2243 | 1724 | 979
Kottayam | 2294 | 1384 | 1381 | 1005 | 757 | 601 | 211
Kozhikode | 7094 | 3552 | 3145 | 3261 | 2132 | 1327 | 264
Malappuaram | 11281 | 5852 | 5740 | 4903 | 3055 | 1883 | 450
Palakkad | 5672 | 3428 | 3267 | 2945 | 1803 | 1247 | 403
Pathanamthitta | 1891 | 894 | 836 | 720 | 501 | 366 | 128
Thiruvananthapuram | 12984 | 7984 | 7732 | 6789 | 4059 | 2479 | 971
Thrissur | 7099 | 4170 | 3962 | 3551 | 2471 | 1740 | 565
Wayanad | 3403 | 1313 | 1265 | 1143 | 690 | 414 | 131
(blank) | 82487 | 45244 | 43167 | 38733 | 25626 | 17520 | 6159
Grand Total | 164974 | 90488 | 86334 | 77466 | 51252 | 35040 | 12318

## Sheet1 (hidden)
Sl.No | District | Project Phase | City | No of beneficiaries | Enrolled | issued building permit | Agreement executed | 1st | 2nd | 3rd | 4th
8 | Alappuzha | Alappuzha1 | Alappuzha | 2278 | 1378 | 1284 | 1162 | 1083 | 926 | 685 | 89
199 | Alappuzha | Alappuzha2 | Alappuzha | 805 | 805 | 459 | 459 | 127 | 5 | 0 | 0
247 | Alappuzha | Alappuzha3 | Alappuzha | 196 | 190 | 52 | 70 | 12 | 0 | 0 | 0
299 | Alappuzha | Alappuzha4 | Alappuzha | 500 | 500 | 223 | 211 | 14
77 | Alappuzha | Chengannur1 | Chengannur | 62 | 62 | 36 | 34 | 32 | 22 | 13 | 3
123 | Alappuzha | Chengannur2 | Chengannur | 73 | 54 | 23 | 19 | 18 | 11 | 3 | 0
202 | Alappuzha | Chengannur3 | Chengannur | 9 | 7 | 4 | 3 | 3 | 2 | 0 | 0
23 | Alappuzha | Cherthala1 | Cherthala | 100 | 93 | 92 | 92 | 88 | 83 | 71 | 18
124 | Alappuzha | Cherthala2 | Cherthala | 367 | 342 | 231 | 231 | 231 | 137 | 47 | 0
204 | Alappuzha | Cherthala3 | Cherthala | 54 | 50 | 18 | 18 | 18 | 4 | 0 | 0
78 | Alappuzha | Haripad1 | Haripad | 58 | 45 | 40 | 38 | 35 | 22 | 12 | 1
209 | Alappuzha | Haripad2 | Haripad | 208 | 196 | 148 | 116 | 91 | 23 | 0
256 | Alappuzha | Haripad3 | Haripad | 124 | 110 | 41 | 11 | 4 | 0 | 0 | 0
12 | Alappuzha | Kayamkulam1 | Kayamkulam | 305 | 250 | 225 | 216 | 214 | 191 | 174 | 140
125 | Alappuzha | Kayamkulam2 | Kayamkulam | 239 | 150 | 145 | 141 | 135 | 115 | 79 | 28
300 | Alappuzha | Kayamkulam3 | Kayamkulam | 160 | 150 | 80 | 79 | 75 | 32 | 4 | 1
24 | Alappuzha | Mavelikkara1 | Mavelikkara | 80 | 80 | 69 | 61 | 59 | 54 | 52 | 34
126 | Alappuzha | Mavelikkara2 | Mavelikkara | 115 | 115 | 59 | 49 | 47 | 35 | 18 | 2
226 | Alappuzha | Mavelikkara3 | Mavelikkara | 7 | 7 | 3 | 3 | 2 | 1 | 1 | 0
25 | Eranakulam | Aluva1 | Aluva | 31 | 14 | 14 | 14 | 13 | 13 | 4 | 4
127 | Eranakulam | Aluva2 | Aluva | 32 | 15 | 14 | 14 | 14 | 7 | 9 | 1
26 | Eranakulam | Angamaly1 | Angamaly | 41 | 28 | 24 | 23 | 22 | 18 | 15 | 7
128 | Eranakulam | Angamaly2 | Angamaly | 74 | 60 | 48 | 46 | 47 | 39 | 26 | 10
200 | Eranakulam | Angamaly3 | Angamaly | 16 | 14 | 13 | 13 | 13 | 10 | 4 | 1
27 | Eranakulam | Eloor1 | Eloor | 42 | 25 | 25 | 25 | 25 | 20 | 20 | 10
129 | Eranakulam | Eloor2 | Eloor | 50 | 39 | 39 | 35 | 35 | 28 | 23 | 8
253 | Eranakulam | Eloor3 | Eloor | 56 | 18 | 18 | 18 | 18 | 7 | 2 | 0
28 | Eranakulam | Kalamassery1 | Kalamassery | 249 | 161 | 152 | 147 | 146 | 127 | 119 | 82
95 | Eranakulam | Kalamassery2 | Kalamassery | 242 | 85 | 78 | 73 | 70 | 39 | 29 | 5
130 | Eranakulam | Kalamassery3 | Kalamassery | 86 | 34 | 24 | 22 | 21 | 7 | 7 | 3
211 | Eranakulam | Kalamassery4 | Kalamassery | 39 | 22 | 21 | 21 | 18 | 8 | 4 | 0
259 | Eranakulam | Kalamassery5 | Kalamassery | 25 | 19 | 17 | 16 | 14 | 10 | 3 | 0
29 | Eranakulam | Koohtattukulam1 | Koohtattukulam | 161 | 160 | 108 | 108 | 108 | 88 | 81 | 32
97 | Eranakulam | Koohtattukulam2 | Koohtattukulam | 51 | 49 | 32 | 31 | 31 | 14 | 9 | 0
131 | Eranakulam | Koohtattukulam3 | Koohtattukulam | 51 | 49 | 14 | 13 | 13 | 2 | 0 | 0
269 | Eranakulam | Koohtattukulam4 | Koohtattukulam | 13 | 13 | 3 | 3 | 3 | 0 | 0 | 0
30 | Eranakulam | Kothamangalam1 | Kothamangalam | 180 | 111 | 110 | 110 | 106 | 96 | 72 | 27
132 | Eranakulam | Kothamangalam2 | Kothamangalam | 439 | 151 | 63 | 60 | 59 | 28 | 11 | 1
31 | Eranakulam | Maradu1 | Maradu | 155 | 105 | 91 | 91 | 78 | 76 | 71 | 52
133 | Eranakulam | Maradu2 | Maradu | 200 | 128 | 70 | 70 | 54 | 50 | 40 | 9
224 | Eranakulam | Maradu3 | Maradu | 91 | 65 | 50 | 50 | 40 | 34 | 29 | 5
32 | Eranakulam | Muvattupuzha1 | Muvattupuzha | 90 | 67 | 66 | 66 | 66 | 57 | 56 | 33
134 | Eranakulam | Muvattupuzha2 | Muvattupuzha | 86 | 31 | 30 | 30 | 30 | 28 | 21 | 15
33 | Eranakulam | N.Paravur1 | N.Paravur | 106 | 95 | 95 | 93 | 91 | 86 | 75 | 34
135 | Eranakulam | N.Paravur2 | N.Paravur | 176 | 80 | 80 | 47 | 43 | 30 | 10 | 0
276 | Eranakulam | N.Paravur3 | N.Paravur | 23 | 12 | 12 | 4 | 1 | 1 | 0 | 0
34 | Eranakulam | Perumbavoor1 | Perumbavoor | 64 | 52 | 52 | 52 | 52 | 48 | 43 | 19
136 | Eranakulam | Perumbavoor2 | Perumbavoor | 64 | 31 | 3o | 30 | 26 | 22 | 11 | 2
287 | Eranakulam | Perumbavoor3 | Perumbavoor | 11 | 7 | 7 | 6 | 6 | 1 | 0 | 0
35 | Eranakulam | Piravom1 | Piravom | 123 | 123 | 97 | 97 | 97 | 88 | 76 | 13
137 | Eranakulam | Piravom2 | Piravom | 63 | 63 | 40 | 39 | 39 | 22 | 23 | 0
288 | Eranakulam | Piravom3 | Piravom | 59 | 59 | 25 | 24 | 24 | 1 | 0 | 0
36 | Eranakulam | Thrikakara1 | Thrikakara | 133 | 94 | 81 | 76 | 76 | 73 | 71 | 47
138 | Eranakulam | Thrikakara2 | Thrikakara | 62 | 45 | 34 | 33 | 33 | 26 | 16 | 3
242 | Eranakulam | Thrikakara3 | Thrikakara | 50 | 34 | 21 | 15 | 15 | 10 | 5 | 0
14 | Eranakulam | Thripunithura1 | Thripunithura | 240 | 225 | 173 | 173 | 173 | 162 | 158 | 93
79 | Eranakulam | Thripunithura2 | Thripunithura | 51 | 48 | 28 | 28 | 28 | 23 | 22 | 6
98 | Eranakulam | Thripunithura3 | Thripunithura | 109 | 93 | 50 | 50 | 50 | 41 | 34 | 1
139 | Eranakulam | Thripunithura4 | Thripunithura | 211 | 173 | 35 | 35 | 35 | 20 | 8 | 0
243 | Eranakulam | Thripunithura5 | Thripunithura | 150 | 120 | 19 | 19 | 19 | 12 | 8 | 0
13 | Eranakulam | Kochi1 | Kochi | 1528 | 1078 | 863 | 863 | 845 | 737 | 672 | 368
96 | Eranakulam | Kochi2 | Kochi | 713 | 451 | 328 | 300 | 271 | 195 | 148 | 40
216 | Eranakulam | Kochi3 | Kochi | 1358 | 450 | 304 | 301 | 276 | 138 | 82 | 4
265 | Eranakulam | Kochi4 | Kochi | 451 | 120 | 111 | 108 | 104 | 43 | 17 | 0
301 | Eranakulam | Kochi5 | Kochi | 734 | 147 | 147 | 145 | 132 | 15 | 0 | 0
37 | Idukki | Kattapana1 | Kattapana | 133 | 131 | 118 | 118 | 116 | 109 | 109 | 68
99 | Idukki | Kattapana2 | Kattapana | 140 | 135 | 111 | 111 | 108 | 82 | 69 | 25
140 | Idukki | Kattapana3 | Kattapana | 422 | 395 | 247 | 247 | 242 | 169 | 133 | 20
215 | Idukki | Kattapana4 | Kattapana | 683 | 587 | 241 | 241 | 219 | 94 | 39 | 2
9 | Idukki | Thodupuzha1 | Thodupuzha | 485 | 414 | 278 | 272 | 272 | 238 | 227 | 189
100 | Idukki | Thodupuzha2 | Thodupuzha | 231 | 218 | 170 | 165 | 165 | 106 | 81 | 15
141 | Idukki | Thodupuzha3 | Thodupuzha | 100 | 95 | 74 | 64 | 64 | 26 | 19 | 2
293 | idukki | Thodupuzha4 | Thodupuzha | 58 | 58 | 45 | 40 | 40 | 10 | 7 | 0
302 | Idukki | Thodupuzha5 | Thodupuzha | 58 | 58 | 39 | 35 | 35 | 5 | 2 | 0
38 | Kannur | Anthoor1 | Anthoor | 202 | 202 | 152 | 152 | 152 | 150 | 140 | 65
142 | Kannur | Anthoor2 | Anthoor | 133 | 133 | 104 | 104 | 104 | 78 | 39 | 0
248 | Kannur | Anthoor3 | Anthoor | 41 | 41 | 34 | 34 | 34 | 11 | 1 | 0
39 | Kannur | Irritty1 | Irritty | 33 | 33 | 29 | 29 | 29 | 28 | 22 | 11
210 | Kannur | Irritty2 | Irritty | 370 | 358 | 186 | 160 | 154 | 87 | 38
258 | Kannur | Irritty3 | Irritty | 44 | 44 | 4 | 2 | 2 | 1
303 | Kannur | Irritty4 | Irritty | 24 | 24 | 1 | 1 | 1
40 | Kannur | Koothuparamba1 | Koothuparamba | 279 | 279 | 202 | 194 | 190 | 168 | 137 | 32
101 | Kannur | Koothuparamba2 | Koothuparamba | 131 | 131 | 46 | 45 | 45 | 11 | 3 | 0
41 | Kannur | Mattannur1 | Mattannur | 123 | 123 | 116 | 107 | 107 | 96 | 73 | 12
225 | Kannur | Mattannur2 | Mattannur | 199 | 199 | 145 | 145 | 145 | 113 | 54 | 2
275 | Kannur | Mattannur3 | Mattannur | 34 | 34 | 19 | 17 | 17 | 16 | 2 | 0
42 | Kannur | Panoor1 | Panoor | 207 | 207 | 138 | 134 | 133 | 116 | 80 | 13
102 | Kannur | Panoor2 | Panoor | 170 | 159 | 91 | 89 | 88 | 49 | 6 | 0
144 | Kannur | Panoor3 | Panoor | 46 | 43 | 21 | 20 | 20 | 11 | 3 | 1
43 | Kannur | Payyannur1 | Payyannur | 247 | 219 | 215 | 215 | 215 | 213 | 142 | 48
145 | Kannur | Payyannur2 | Payyannur | 163 | 144 | 130 | 126 | 126 | 81 | 21 | 0
234 | Kannur | Payyannur3 | Payyannur | 141 | 119 | 114 | 113 | 110 | 69 | 17 | 0
284 | Kannur | Payyannur4 | Payyannur | 12 | 9 | 8 | 8 | 8 | 3 | 0 | 0
305 | Kannur | Payyannur5 | Payyannur | 60 | 53 | 50 | 46 | 46 | 3 | 0
44 | Kannur | Sreekandapuram1 | Sreekandapuram | 167 | 167 | 150 | 150 | 144 | 137 | 114 | 29
146 | Kannur | Sreekandapuram2 | Sreekandapuram | 100 | 100 | 83 | 82 | 69 | 42 | 13 | 1
291 | Kannur | Sreekandapuram3 | Sreekandapuram | 253 | 247 | 128 | 126 | 40 | 0 | 0 | 0
15 | Kannur | Thalassery1 | Thalassery | 210 | 172 | 143 | 139 | 137 | 117 | 94 | 36
104 | Kannur | Thalassery2 | Thalassery | 33 | 32 | 18 | 16 | 17 | 13 | 7 | 0
147 | Kannur | Thalassery3 | Thalassery | 30 | 29 | 13 | 12 | 12 | 7 | 2 | 0
306 | Kannur | Thalassery4 | Thalassery | 29 | 29 | 22 | 21 | 21 | 4 | 0 | 0
45 | Kannur | Thalipparamba 1 | Thalipparamba | 190 | 190 | 157 | 157 | 157 | 141 | 125 | 67
103 | Kannur | Thalipparamba 2 | Thalipparamba | 76 | 76 | 53 | 53 | 53 | 45 | 13 | 2
240 | Kannur | Thalipparamba 3 | Thalipparamba | 25 | 25 | 16 | 17 | 17 | 14 | 2 | 0
1 | Kannur | Kannur1 | Kannur | 491 | 360 | 340 | 332 | 332 | 260 | 210 | 86
143 | Kannur | Kannur2 | Kannur | 38 | 36 | 24 | 22 | 22 | 5 | 1 | 0
262 | Kannur | Kannur3 | Kannur | 357 | 300 | 260 | 257 | 257 | 57 | 3 | 0
304 | Kannur | Kannur4 | Kannur | 54 | 49 | 39 | 38 | 38 | 3
46 | Kasaragod | Kanhangad1 | Kanhangad | 530 | 530 | 349 | 345 | 339 | 272 | 169 | 47
213 | Kasaragod | Kanhangad2 | Kanhangad | 409 | 404 | 170 | 169 | 173 | 110 | 44 | 0
261 | Kasaragod | Kanhangad3 | Kanhangad | 211 | 139 | 76 | 70 | 68 | 39 | 10 | 0
2 | Kasaragod | Kasaragod1 | Kasaragod | 167 | 147 | 102 | 102 | 101 | 85 | 75 | 23
148 | Kasaragod | Kasaragod2 | Kasaragod | 32 | 26 | 9 | 9 | 3 | 1 | 0 | 0
214 | Kasaragod | Kasaragod3 | Kasaragod | 10 | 2 | 2 | 2 | 2 | 0 | 0 | 0
264 | Kasaragod | Kasaragod4 | Kasaragod | 153 | 96 | 13 | 13 | 3 | 2 | 0 | 0
47 | Kasaragod | Nileswaram1 | Nileswaram | 153 | 153 | 148 | 142 | 140 | 140 | 100 | 10
149 | Kasaragod | Nileswaram2 | Nileswaram | 298 | 297 | 137 | 101 | 99 | 15 | 0 | 0
228 | Kasaragod | Nileswaram3 | Nileswaram | 153 | 145 | 32 | 12 | 12 | 0 | 0 | 0
279 | Kasaragod | Nileswaram4 | Nileswaram | 82 | 55 | 20 | 0 | 0 | 0 | 0 | 0
48 | Kollam | Karunagappally1 | Karunagappally | 215 | 215 | 166 | 166 | 161 | 120 | 86 | 65
105 | Kollam | Karunagappally2 | Karunagappally | 187 | 187 | 108 | 108 | 70 | 34 | 14 | 4
150 | Kollam | Karunagappally3 | Karunagappally | 124 | 124 | 52 | 52 | 52 | 14 | 8 | 1
263 | Kollam | Karunagappally4 | Karunagappally | 36 | 36 | 10 | 10 | 10 | 0 | 0 | 0
49 | Kollam | Kottarakkara1 | Kottarakkara | 140 | 140 | 100 | 100 | 96 | 69 | 50 | 10
152 | Kollam | Kottarakkara2 | Kottarakkara | 151 | 151 | 102 | 96 | 90 | 58 | 42 | 3
219 | Kollam | Kottarakkara3 | Kottarakkara | 32 | 32 | 23 | 18 | 14 | 7 | 6 | 0
307 | Kollam | Kottarakkara4 | Kottarakkara | 81 | 81 | 65 | 53 | 37 | 0 | 0 | 0
50 | Kollam | Punalur1 | Punalur | 200 | 200 | 184 | 184 | 184 | 176 | 171 | 112
153 | Kollam | Punalur2 | Punalur | 837 | 837 | 660 | 658 | 376 | 0 | 0 | 0
236 | Kollam | Punalur3 | Punalur | 118 | 118 | 68 | 68 | 25 | 0 | 0 | 0
51 | Kollam | South Paravoor1 | South Paravoor | 315 | 288 | 277 | 277 | 260 | 260 | 229 | 133
107 | Kollam | South Paravoor2 | South Paravoor | 197 | 145 | 119 | 119 | 118 | 65 | 22
154 | Kollam | South Paravoor3 | South Paravoor | 84 | 55 | 49 | 49 | 12 | 9 | 6 | 1
10 | Kollam | Kollam1 | Kollam | 1422 | 1422 | 725 | 723 | 715 | 628 | 568 | 430
106 | Kollam | Kollam2 | Kollam | 340 | 225 | 242 | 238 | 237 | 212 | 190 | 126
151 | Kollam | Kollam3 | Kollam | 1125 | 1125 | 800 | 594 | 615 | 438 | 287 | 93
217 | Kollam | Kollam4 | Kollam | 243 | 243 | 150 | 82 | 81 | 52 | 27 | 1
268 | Kollam | Kollam5 | Kollam | 983 | 426 | 177 | 173 | 252 | 101 | 18 | 0
52 | Kottayam | Changanassery1 | Changanassery | 62 | 27 | 27 | 27 | 27 | 16 | 14 | 4
155 | Kottayam | Changanassery2 | Changanassery | 131 | 52 | 52 | 52 | 52 | 31 | 23 | 2
251 | Kottayam | Changanassery3 | Changanassery | 55 | 25 | 25 | 25 | 25 | 10 | 3 | 0
53 | Kottayam | Erattupetta1 | Erattupetta | 165 | 143 | 143 | 143 | 141 | 140 | 140 | 66
156 | Kottayam | Erattupetta2 | Erattupetta | 337 | 315 | 209 | 209
206 | Kottayam | Erattupetta3 | Erattupetta | 62 | 62 | 41 | 41
308 | Kottayam | Erattupetta4 | Erattupetta | 141 | 126 | 80 | 80
80 | Kottayam | Ettumanoor1 | Ettumanoor | 198 | 180 | 131 | 131 | 127 | 102 | 81 | 45
157 | Kottayam | Ettumanoor2 | Ettumanoor | 148 | 120 | 87 | 87 | 87 | 50 | 30 | 6
207 | Kottayam | Ettumanoor3 | Ettumanoor | 19 | 15 | 11 | 11 | 11 | 10 | 5 | 0
254 | Kottayam | Ettumanoor4 | Ettumanoor | 24 | 14 | 10 | 10 | 10 | 5 | 4 | 0
54 | Kottayam | Kottayam1 | Kottayam | 335 | 308 | 195 | 194 | 194 | 168 | 146 | 67
158 | Kottayam | Kottayam2 | Kottayam | 156 | 153 | 83 | 81 | 78 | 59 | 41 | 6
220 | Kottayam | Kottayam3 | Kottayam | 187 | 187 | 88 | 88 | 89 | 60 | 31 | 3
81 | Kottayam | Palai1 | Palai | 14 | 11 | 11 | 11 | 10 | 10 | 9 | 3
159 | Kottayam | Palai2 | Palai | 18 | 18 | 18 | 18 | 14 | 12 | 9 | 3
281 | Kottayam | Palai3 | Palai | 19 | 18 | 18 | 18 | 9 | 3 | 2 | 0
309 | Kottayam | Palai4 | Palai | 24 | 23 | 23 | 23 | 11 | 1 | 0 | 0
82 | Kottayam | Vaikom1 | Vaikom | 34 | 30 | 30 | 30 | 30 | 27 | 27 | 4
160 | Kottayam | Vaikom2 | Vaikom | 148 | 128 | 92 | 92 | 81 | 51 | 35 | 2
246 | Kottayam | Vaikom3 | Vaikom | 17 | 10 | 10 | 10 | 9 | 2 | 1 | 0
55 | Kozhikode | Feroke1 | Feroke | 217 | 217 | 195 | 182 | 180 | 159 | 145 | 11
208 | Kozhikode | Feroke2 | Feroke | 190 | 190 | 162 | 155 | 151 | 63 | 17 | 0
83 | kozhikode | Koduvally1 | Koduvally | 49 | 42 | 42 | 42 | 42 | 41 | 20 | 0
161 | Kozhikode | Koduvally2 | Koduvally | 501 | 402 | 345 | 345 | 322 | 248 | 127 | 4
267 | Kozhikode | Koduvally3 | Koduvally | 153 | 123 | 109 | 109 | 102 | 38 | 3 | 0
310 | kozhikode | Koduvally4 | Koduvally | 82 | 65 | 52 | 52 | 50 | 12 | 2 | 0
56 | Kozhikode | Mukkom1 | Mukkom | 126 | 126 | 126 | 121 | 121 | 120 | 113 | 96
163 | Kozhikode | Mukkom2 | Mukkom | 184 | 183 | 183 | 178 | 178 | 170 | 153 | 76
227 | Kozhikode | Mukkom3 | Mukkom | 66 | 66 | 51 | 51 | 49 | 41 | 28 | 4
84 | Kozhikode | Payyoli1 | Payyoli | 102 | 102 | 86 | 85 | 85 | 58 | 25 | 2
164 | Kozhikode | Payyoli2 | Payyoli | 220 | 220 | 82 | 82 | 82 | 18 | 1 | 0
285 | Kozhikode | Payyoli3 | Payyoli | 345 | 345 | 33 | 32 | 30 | 2 | 1 | 0
312 | Kozhikode | Payyoli4 | Payyoli | 120 | 120 | 13 | 12 | 11 | 3 | 0 | 0
57 | Kozhikode | Quilandy1 | Quilandy | 633 | 633 | 394 | 388 | 378 | 290 | 173 | 5
165 | Kozhikode | Quilandy2 | Quilandy | 274 | 252 | 22 | 19 | 15 | 0 | 0 | 0
237 | Kozhikode | Quilandy3 | Quilandy | 39 | 32 | 6 | 4 | 2 | 0 | 0 | 0
85 | Kozhikode | Ramanattukara1 | Ramanattukara | 64 | 64 | 57 | 57 | 57 | 54 | 51 | 3
166 | Kozhikode | Ramanattukara2 | Ramanattukara | 143 | 143 | 94 | 94 | 91 | 70 | 36 | 2
238 | Kozhikode | Ramanattukara3 | Ramanattukara | 35 | 35 | 17 | 17 | 17 | 13 | 4 | 0
16 | Kozhikode | Vadakara1 | Vadakara | 270 | 270 | 190 |  | 186 | 160 | 111 | 15
167 | Kozhikode | Vadakara2 | Vadakara | 260 | 260 | 115 | 113 | 113 | 61 | 7 | 3
297 | Kozhikode | Vadakara3 | Vadakara | 12 | 12 | 6 | 5 | 5 | 0 | 0 | 0
11 | Kozhikode | Kozhikode1 | Kozhikode | 1783 | 814 | 426 | 391 | 391 | 286 | 240 | 43
162 | Kozhikode | Kozhikode2 | Kozhikode | 289 | 254 | 159 | 149 | 141 | 93 | 32 | 0
221 | Kozhikode | Kozhikode3 | Kozhikode | 320 | 292 | 203 | 163 | 163 | 96 | 37 | 0
271 | kozhikode | Kozhikode4 | Kozhikode | 416 | 394 | 234 | 190 | 190 | 27 | 1 | 0
311 | Kozhikode | Kozhikode5 | Kozhikode | 201 | 201 | 150 | 109 | 109 | 9 | 0 | 0
86 | Malappuaram | Kondotty1 | Kondotty | 603 | 591 | 367 | 352 | 352 | 301 | 262 | 139
168 | Malappuaram | Kondotty2 | Kondotty | 239 | 234 | 132 | 124 | 124 | 31 | 11 | 1
87 | Malappuaram | Kottakkal1 | Kottakkal | 45 | 45 | 36 | 35 | 35 | 35 | 31 | 4
169 | Malappuaram | Kottakkal2 | Kottakkal | 148 | 148 | 77 | 77 | 73 | 71 | 20 | 0
218 | Malappuaram | Kottakkal3 | Kottakkal | 38 | 38 | 17 | 17 | 16 | 13 | 1 | 0
270 | Malappuaram | Kottakkal4 | Kottakkal | 13 | 13 | 8 | 8 | 8 | 4 | 0 | 0
3 | Malappuaram | Malappuram1 | Malappuram | 477 | 477 | 379 | 379 | 371 | 335 | 291 | 94
17 | Malappuaram | Malappuram2 | Malappuram | 229 | 229 | 174 | 174 | 167 | 155 | 135 | 41
108 | Malappuaram | Malappuram3 | Malappuram | 207 | 207 | 133 | 133 | 123 | 81 | 20 | 1
170 | Malappuaram | Malappuram4 | Malappuram | 225 | 225 | 147 | 147 | 128 | 35 | 2 | 0
223 | Malappuaram | Malappuram5 | Malappuram | 148 | 148 | 72 | 72 | 55 | 0 | 0 | 0
272 | Malappuaram | Malappuram6 | Malappuram | 75 | 75 | 28 | 28 | 20 | 0 | 0 | 0
313 | Malappuaram | Malappuram7 | Malappuram | 108 | 108 | 43 | 43 | 14 | 0 | 0 | 0
18 | Malappuaram | Manjeri1 | Manjeri | 530 | 529 | 466 | 466 | 465 | 430 | 379 | 44
171 | Malappuaram | Manjeri2 | Manjeri | 490 | 490 | 356 | 356 | 336 | 69 | 0 | 0
273 | Malappuaram | Manjeri3 | Manjeri | 261 | 261 | 191 | 191 | 0 | 0 | 0 | 0
314 | Malappuaram | Manjeri4 | Manjeri | 195 | 182 | 138 | 138 | 0 | 0 | 0 | 0
110 | Malappuaram | Nilambur1 | Nilambur | 72 | 66 | 47 | 47 | 46 | 46 | 37 | 9
175 | Malappuaram | Nilambur2 | Nilambur | 190 | 166 | 113 | 113 | 113 | 53 | 16 | 0
278 | Malappuaram | Nilambur3 | Nilambur | 110 | 102 | 36 | 36 | 28 | 2 | 2 | 0
111 | Malappuaram | Parappanangady 1 | Parappanangady | 56 | 56 | 53 | 53 | 53 | 41 | 13 | 1
176 | Malappuaram | Parappanangady 2 | Parappanangady | 259 | 259 | 146 | 146 | 91 | 32 | 10 | 1
231 | Malappuaram | Parappanangady 3 | Parappanangady | 396 | 396 | 131 | 131 | 46 | 0 | 0 | 0
315 | Malappuaram | Parappanangady 4 | Parappanangady | 220 | 170 | 42 | 42 | 0 | 0 | 0
88 | Malappuaram | Perinthalmanna1 | Perinthalmanna | 98 | 94 | 86 | 86 | 86 | 85 | 72 | 8
109 | Malappuaram | Perinthalmanna2 | Perinthalmanna | 358 | 340 | 209 | 201 | 201 | 76 | 22 | 0
235 | Malappuaram | Perinthalmanna3 | Perinthalmanna | 730 | 650 | 71 | 67 | 29 | 10 | 0 | 0
286 | Malappuaram | Perinthalmanna4 | Perinthalmanna | 52 | 49 | 8 | 5 | 5 | 0 | 0 | 0
316 | Malappuaram | Perinthalmanna5 | Perinthalmanna | 136 | 110 | 8 | 3 | 3 | 0 | 0 | 0
58 | Malappuaram | Ponnani1 | Ponnani | 563 | 563 | 356 | 352 | 340 | 279 | 215 | 65
89 | Malappuaram | Ponnani2 | Ponnani | 192 | 192 | 125 | 115 | 115 | 58 | 41 | 10
172 | Malappuaram | Ponnani3 | Ponnani | 293 | 293 | 149 | 149 | 136 | 83 | 53 | 4
289 | Malappuaram | Ponnani4 | Ponnani | 208 | 208 | 60 | 59 | 51 | 22 | 6 | 0
317 | Malappuaram | Ponnani5 | Ponnani | 120 | 120 | 28 | 16 | 16 | 1 | 0 | 0
91 | Malappuaram | Thanur1 | Thanur | 1123 | 1123 | 710 | 710 | 662 | 344 | 50 | 0
174 | Malappuaram | Thanur2 | Thanur | 448 | 448 | 16 | 16 | 0 | 0 | 0 | 0
241 | Malappuaram | Thanur3 | Thanur | 105 | 80 | 4 | 4 | 0 | 0 | 0 | 0
59 | Malappuaram | Tirur1 | Tirur | 80 |  | 67 | 67 | 65 | 64 | 43 | 14
173 | Malappuaram | Tirur2 | Tirur | 210 | 210 | 98 | 91 | 90 | 46 | 12 | 0
244 | Malappuaram | Tirur3 | Tirur | 80 | 80 | 27 | 26 | 10 | 0 | 0 | 0
295 | Malappuaram | Tirur4 | Tirur | 338 | 127 | 17 | 17 | 0 | 0 | 0 | 0
90 | Malappuaram | Tirurangadi1 | Tirurangadi | 47 | 41 | 41 | 41 | 41 | 41 | 40 | 9
245 | Malappuaram | Tirurangadi2 | Tirurangadi | 213 | 209 | 117 | 115 | 112 | 90 | 0 | 0
296 | Malappuaram | Tirurangadi3 | Tirurangadi | 83 | 81 | 14 | 13 | 9 | 0 | 0 | 0
318 | Malappuaram | Tirurangadi4 | Tirurangadi | 53 | 51 | 11 | 9 | 5 | 0 | 0 | 0
112 | Malappuaram | Valanchery1 | Valanchery | 249 | 247 | 212 | 184 | 183 | 117 | 99 | 5
113 | Malappuaram | Valanchery2 | Valanchery | 66 | 66 | 34 | 34 | 28 | 3 | 0
298 | Malappuaram | Valanchery3 | Valanchery | 79 | 72 | 35 | 35 | 34 | 2 | 0 | 0
319 | Malappuaram | Valanchery4 | Valanchery | 23 | 23 | 17 | 17 | 18 | 0 | 0 | 0
60 | Palakkad | Cherplassery1 | Cherplassery | 100 | 100 | 100 | 100 | 100 | 96 | 95 | 48
203 | Palakkad | Cherplassery2 | Cherplassery | 374 | 347 | 248 | 164 | 164 | 0 | 0 | 0
61 | Palakkad | Chittur-Thathamangalam1 | Chittur-Thathamangalam | 314 | 233 | 233 | 233 | 233 | 198 | 170 | 49
177 | Palakkad | Chittur-Thathamangalam2 | Chittur-Thathamangalam | 209 | 209 | 86 | 86 | 86 | 32 | 7 | 0
205 | Palakkad | Chittur-Thathamangalam3 | Chittur-Thathamangalam | 45 | 20 | 20 | 16 | 16 | 6 | 1 | 0
252 | Palakkad | Chittur-Thathamangalam4 | Chittur-Thathamangalam | 50 | 19 | 19 | 19 | 19 | 4 | 1 | 0
62 | Palakkad | Mannarkkad1 | Mannarkkad | 124 | 124 | 124 | 121 | 121 | 119 | 116 | 86
178 | Palakkad | Mannarkkad2 | Mannarkkad | 430 | 430 | 370 | 370 | 321 | 0 | 0 | 0
274 | Palakkad | Mannarkkad3 | Mannarkkad | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | Palakkad | Ottappalam1 | Ottappalam | 426 | 426 | 302 | 302 | 302 | 290 | 245 | 79
179 | Palakkad | Ottappalam2 | Ottappalam | 327 | 327 | 224 | 242 | 68 | 0 | 0 | 0
280 | Palakkad | Ottappalam3 | Ottappalam | 146 | 0 | 49 | 49 | 1 | 0 | 0 | 0
4 | Palakkad | Palakkad1 | Palakkad | 605 | 315 | 325 | 315 | 313 | 245 | 205 | 78
114 | Palakkad | Palakkad2 | Palakkad | 343 | 160 | 172 | 160 | 156 | 117 | 70 | 4
115 | Palakkad | Palakkad3 | Palakkad | 381 | 130 | 139 | 130 | 129 | 80 | 44 | 1
229 | Palakkad | Palakkad4 | Palakkad | 259 | 87 | 100 | 87 | 85 | 48 | 20 | 2
282 | Palakkad | Palakkad5 | Palakkad | 161 | 45 | 69 | 45 | 44 | 20 | 6 | 0
320 | Palakkad | Palakkad6 | Palakkad | 123 | 30 | 36 | 30 | 27 | 1 | 0 | 0
64 | Palakkad | Pattambi1 | Pattambi | 181 | 181 | 145 | 145 | 145 | 141 | 125 | 34
116 | Palakkad | Pattambi2 | Pattambi | 95 | 95 | 64 | 64 | 64 | 52 | 26 | 0
180 | Palakkad | Pattambi3 | Pattambi | 175 | 175 | 119 | 119 | 119 | 94 | 20 | 0
233 | Palakkad | Pattambi4 | Pattambi | 53 | 53 | 22 | 22 | 22 | 10 | 2 | 0
65 | Palakkad | Shoranur1 | Shoranur | 66 | 62 | 62 | 62 | 62 | 61 | 49 | 19
117 | Palakkad | Shoranur2 | Shoranur | 401 | 350 | 235 | 229 | 217 | 139 | 35 | 3
181 | Palakkad | Shoranur3 | Shoranur | 118 | 111 | 70 | 65 | 54 | 20 | 5 | 0
290 | Palakkad | Shoranur4 | Shoranur | 128 | 121 | 95 | 92 | 77 | 30 | 5 | 0
92 | Pathanamthitta | Adoor1 | Adoor | 47 | 47 | 40 | 40 | 40 | 37 | 28 | 10
198 | Pathanamthitta | Adoor2 | Adoor | 59 | 59 | 51 | 51 | 51 | 33 | 14 | 0
321 | Pathanamthitta | Adoor3 | Adoor | 52 | 52 | 30 | 30 | 30
67 | Pathanamthitta | Pandalam1 | Pandalam | 102 | 96 | 72 | 72 | 72 | 67 | 65 | 5
183 | Pathanamthitta | Pandalam2 | Pandalam | 309 | 232 | 130 | 120 | 89 | 52 | 29 | 0
230 | Pathanamthitta | Pandalam3 | Pandalam | 172 | 94 | 80 | 60 | 19 | 6 | 6 | 0
283 | Pathanamthitta | Pandalam4 | Pandalam | 91 | 88 | 40 | 35 | 14 | 5 | 1 | 0
5 | Pathanamthitta | Pathanamthitta1 | Pathanamthitta | 213 | 213 | 123 | 123 | 123 | 110 | 103 | 79
182 | Pathanamthitta | Pathanamthitta2 | Pathanamthitta | 367 | 202 | 155 | 140 | 119 | 63 | 25 | 1
232 | Pathanamthitta | Pathanamthitta3 | Pathanamthitta | 69 | 20 | 10 | 2
20 | Pathanamthitta | Thiruvalla1 | Thiruvalla | 361 | 147 | 147 | 147 | 147 | 124 | 93 | 33
197 | Pathanamthitta | Thiruvalla2 | Thiruvalla | 49 | 39 | 16 | 16 | 16 | 4 | 2 | 0
66 | Thiruvananthapuram | Attingal1 | Attingal | 40 | 40 | 36 | 35 | 35 | 34 | 34 | 26
118 | Thiruvananthapuram | Attingal2 | Attingal | 34 | 34 | 29 | 29 | 29 | 29 | 23 | 4
184 | Thiruvananthapuram | Attingal3 | Attingal | 58 | 58 | 48 | 47 | 44 | 36 | 19
201 | Thiruvananthapuram | Attingal4 | Attingal | 22 | 22 | 16 | 14 | 10 | 9 | 1
249 | Thiruvananthapuram | Attingal5 | Attingal | 25 | 23 | 20 | 16 | 11 | 8 | 1
19 | Thiruvananthapuram | Nedumangadu1 | Nedumangadu | 850 | 843 | 771 | 771 | 771 | 758 | 722 | 500
119 | Thiruvananthapuram | Nedumangadu2 | Nedumangadu | 542 | 511 | 396 | 369 | 369 | 0 | 0 | 0
277 | Thiruvananthapuram | Nedumangadu3 | Nedumangadu | 818 | 700 | 57 | 0 | 0 | 0 | 0 | 0
322 | Thiruvananthapuram | Nedumangadu4 | Nedumangadu | 128 | 126 | 4 | 0 | 0 | 0 | 0 | 0
68 | Thiruvananthapuram | Neyyattinkara1 | Neyyattinkara | 500 | 469 | 449 | 449 | 449 | 433 | 416 | 219
185 | Thiruvananthapuram | Neyyattinkara2 | Neyyattinkara | 1668 | 1174 | 739 | 722 | 531 | 88 | 0 | 0
70 | Thiruvananthapuram | Varkala1 | Varkala | 261 | 261 | 177 | 177 | 174 | 146 | 126 | 78
121 | Thiruvananthapuram | Varkala2 | Varkala | 123 | 123 | 112 | 112 | 111 | 97 | 73 | 18
187 | Thiruvananthapuram | Varkala3 | Varkala | 38 | 38 | 24 | 24 | 24 | 17 | 11 | 1
69 | Thiruvananthapuram | Thiruvananthapuram1 | Thiruvananthapuram | 1397 | 1397 | 986 | 951 | 926 | 815 | 669 | 124
120 | Thiruvananthapuram | Thiruvananthapuram2 | Thiruvananthapuram | 1862 | 1862 | 1479 | 1442 | 1395 | 923 | 244 | 1
186 | Thiruvananthapuram | Thiruvananthapuram3 | Thiruvananthapuram | 1879 | 1879 | 1265 | 1258 | 1169 | 618 | 139 | 0
292 | Thiruvananthapuram | Thiruvananthapuram4 | Thiruvananthapuram | 2151 | 2151 | 1129 | 1103 | 739 | 48 | 1 | 0
323 | Thiruvananthapuram | Thiruvananthapuram5 | Thiruvananthapuram | 588 | 588 | 247 | 213 | 2 | 0 | 0 | 0
71 | Thrissur | Chalakudy1 | Chalakudy | 78 | 66 | 63 | 61 | 61 | 57 | 56 | 37
188 | Thrissur | Chalakudy2 | Chalakudy | 194 | 159 | 138 | 134 | 134 | 92 | 51 | 4
250 | Thrissur | Chalakudy3 | Chalakudy | 30 | 30 | 23 | 21 | 21 | 9 | 1 | 0
324 | Thrissur | Chalakudy4 | Chalakudy | 39 | 33 | 14 | 13 | 13 | 1 | 0 | 0
21 | Thrissur | Chavakkad1 | Chavakkad | 355 | 355 | 325 | 322 | 322 | 309 | 284 | 107
122 | Thrissur | Chavakkad2 | Chavakkad | 533 | 533 | 90 | 90 | 90 | 52 | 31 | 3
72 | Thrissur | Guruvayoor1 | Guruvayoor | 394 | 394 | 254 | 254 | 243 | 198 | 154 | 50
189 | Thrissur | Guruvayoor2 | Guruvayoor | 108 | 108 | 79 | 79 | 74 | 44 | 16 | 0
255 | Thrissur | Guruvayoor3 | Guruvayoor | 176 | 176 | 110 | 110 | 96 | 25 | 6 | 0
73 | Thrissur | Irinjalakuda1 | Irinjalakuda | 184 | 184 | 154 | 154 | 154 | 154 | 134 | 75
190 | Thrissur | Irinjalakuda2 | Irinjalakuda | 219 | 219 | 155 | 155 | 155 | 131 | 65 | 9
257 | Thrissur | Irinjalakuda3 | Irinjalakuda | 27 | 27 | 14 | 14 | 14 | 8 | 5 | 1
325 | Thrissur | Irinjalakuda4 | Irinjalakuda | 120 | 120 | 84 | 84 | 84 | 43 | 6 | 0
74 | Thrissur | Kodungallur1 | Kodungallur | 169 | 169 | 147 | 147 | 146 | 137 | 133 | 83
191 | Thrissur | Kodungallur2 | Kodungallur | 755 | 755 | 385 | 315 | 199 | 94 | 48 | 0
266 | Thrissur | Kodungallur3 | Kodungallur | 98 | 98 | 31 | 20 | 7 | 0 | 0 | 0
326 | Thrissur | Kodungallur4 | Kodungallur | 47 | 47 | 26 | 20 | 5 | 0 | 0 | 0
75 | Thrissur | Kunnamkulam1 | Kunnamkulam | 258 | 258 | 191 | 191 | 191 | 155 | 123 | 35
222 | Thrissur | Kunnamkulam2 | Kunnamkulam | 332 | 332 | 215 | 215 | 215 | 78 | 9 | 0
327 | Thrissur | Kunnamkulam3 | Kunnamkulam | 505 | 472 | 200 | 190 | 146 | 0 | 0 | 0
76 | Thrissur | Wadakkanchery1 | Wadakkanchery | 659 | 613 | 535 | 526 | 501 | 424 | 310 | 35
193 | Thrissur | Wadakkanchery2 | Wadakkanchery | 580 | 451 | 280 | 261 | 208 | 69 | 0 | 0
328 | Thrissur | Wadakkanchery3 | Wadakkanchery | 245 | 241 | 125 | 114 | 0 | 0 | 0 | 0
6 | Thrissur | Thrissur1 | Thrissur | 270 | 270 | 160 | 151 | 151 | 134 | 119 | 69
22 | Thrissur | Thrissur2 | Thrissur | 204 | 204 | 125 | 108 | 108 | 91 | 76 | 37
192 | Thrissur | Thrissur3 | Thrissur | 491 | 491 | 235 | 202 | 202 | 159 | 111 | 20
294 | Thrissur | Thrissur4 | Thrissur | 29 | 29 | 12 | 11 | 11 | 7 | 2 | 0
7 | Wayanad | Kalpetta1 | Kalpetta | 258 | 258 | 176 | 173 | 173 | 136 | 123 | 86
194 | Wayanad | Kalpetta2 | Kalpetta | 140 | 140 | 105 | 103 | 103 | 64 | 41 | 3
212 | Wayanad | Kalpetta3 | Kalpetta | 67 | 67 | 56 | 55 | 55 | 28 | 16 | 2
260 | Wayanad | Kalpetta4 | Kalpetta | 28 | 28 | 25 | 25 | 25 | 10 | 4 | 0
329 | Wayanad | Kalpetta5 | Kalpetta | 44 | 44 | 40 | 38 | 38 | 3 | 0 | 0
93 | Wayanad | Mananthavady1 | Mananthavady | 360 | 360 | 345 | 342 | 337 | 267 | 133 | 35
195 | Wayanad | Mananthavady2 | Mananthavady | 1528 | 1172 | 190 | 182 | 167 | 0 | 0 | 0
94 | Wayanad | Sulthan Bathery1 | Sulthan Bathery | 175 | 175 | 144 | 142 | 142 | 123 | 87 | 5
196 | Wayanad | Sulthan Bathery2 | Sulthan Bathery | 175 | 175 | 106 | 103 | 103 | 59 | 10 | 0
239 | Wayanad | Sulthan Bathery3 | Sulthan Bathery | 569 | 457 | 102 | 81 | 0 | 0 | 0 | 0
330 | Wayanad | Sulthan Bathery4 | Sulthan Bathery | 59 | 59 | 24 | 21
|  |  |  | 82487 | 70169 | 45244 | 43167 | 38733 | 25626 | 17520 | 6159